## Sheet1
COSC1076 ¦ Semester 1 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: |  |  | Progress Classes: | Ahead
Group Member: | A |  |  | On-track
Group Member: | B |  |  | Behind
Group Member: | C |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Group Formed |  | Weekly Contribution
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
Basic Main menu with "credits"
Choice of where to use linked list, vector & array
|  | Progress | Way Behind
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Initial Design of ADTs (classes and potential methods) |  | Weekly Contribution
|  |  | Main menu |  | Issues
|  |  | User Prompt (for gameplay), but no/minimal error checking |  | Other Notes
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | Way Behind
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
|  | Progress | Way Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution
|  |  | Full error checking of user prompt |  | Issues
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Final Tests
Group Report Written
|  | Progress | Way Behind